## BURNDOWN CHART1
BURNDOWN CHART SPRINT1
Days | Goal | Done | Goal velocity | Remaining
0 | 0 | 0 | 61 | 61
1 | 6 | 5 | 55 | 56
2 | 6 | 8 | 49 | 48
3 | 6 | 10 | 43 | 38
4 | 6 | 6 | 37 | 32
5 | 6 | 5 | 31 | 27
6 | 6 | 4 | 25 | 23
7 | 6 | 3 | 19 | 20
8 | 6 | 2 | 13 | 18
9 | 6 | 0 | 7 | 18
10 | 7 | 0 | 0 | 18
Note on D6: stakeholdermap.com: Change the timescale to suit you needs e.g. Sprint or Iteration.
Note on E6: stakeholdermap.com: Number of features or story points you plan to complete.
Note on H6: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## BURNDOWN CHART2
BURNDOWN CHART SPRINT2
Days | Goal | Done | Goal velocity | Remaining
0 | 0 | 0 | 150 | 150
1 | 7 | 7 | 143 | 143
2 | 7 | 7 | 136 | 136
3 | 7 | 8 | 129 | 128
4 | 7 | 6 | 122 | 122
5 | 7 | 7 | 115 | 115
6 | 7 | 7 | 108 | 108
7 | 7 | 6 | 101 | 102
8 | 7 | 7 | 94 | 95
9 | 7 | 6 | 87 | 89
10 | 7 | 7 | 80 | 82
11 | 7 | 7 | 73 | 75
12 | 7 | 8 | 66 | 67
13 | 7 | 7 | 59 | 60
14 | 7 | 9 | 52 | 51
15 | 7 | 8 | 45 | 43
16 | 7 | 8 | 38 | 35
17 | 7 | 7 | 31 | 28
18 | 7 | 8 | 24 | 20
19 | 7 | 6 | 17 | 14
20 | 8 | 7 | 9 | 7
21 | 9 | 7 | 0 | 0
Note on B8: stakeholdermap.com: Change the timescale to suit you needs e.g. Sprint or Iteration.
Note on C8: stakeholdermap.com: Number of features or story points you plan to complete.
Note on F8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## PROJECT DETAILS
PROJECT NUMBER | 1
PROJECT NAME | hospital management system
PROJECT MANAGER | joud alqazlan
DATE | 22/11/2025
VERSION | 1,2

## INSTRUCTIONS
Instructions
Days
Change this to the timescale that you want to appear at the bottom of the chart (the x axis).
Goal or target
Enter the number of features/story points that you plan to achieve in each time period. This forms the yellow line showing goal velocity on the chart.
Done or actual
Record how many features/story points that you actually achieve.
Goal or target velocity
This is a calculated field that counts down the target points to zero (completion of the project). It forms the left side of the chart (the y axis).
Remaining
This is a calculated field that simply deducts Done from Remaining. It is the blue line showing the actual burndown rate on the chart.