## Project details
PROJECT NAME | Hospital management system
Project Members | Joud alqazlan
Roaa alhumaidi
Sumaiya balatif
Bushra almughirah
DATE | 2025-10-29

## Week 1
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Sumaiya | What did you do yesterday? |  | Attend team meeting. | Wrote the first draft of product vision. | Reviewed the vision with team. | Prepares notes for next Scrum meeting.
| What are doing today? | Sprint up plan. | Finalizing project goal. | Sharing feedback with members. | Organizing presentation points. | Summarizing weekly work.
| Is there anything blocking you? | No | No | No | No | No
Joud | What did you do yesterday? |  | Reviewed user stories. | Created the first sprint Backlog. | Organized tasks by priority. | Updated task status.
| What are doing today? | Following up with team. | Selecting tasks for sprint. | Updating the table. | Checking progress. | Writing summary notes.
| Is there anything blocking you? | No | No | No | No | No
Roaa | What did you do yesterday? |  | Collected requirements from team. | Added items to Product Backlog. | Reviewed task distribution with Busra. | Updated final list.
| What are doing today? | Orgnize backlog. | Assigning task. | Tracking updates. | Reviewing team items. | Reviewing work withtheam.
| Is there anything blocking you? | No | No | No | No | No
Bushra | What did you do yesterday? |  | Helped Roaa distribute tasks. | Checked task status. | Followed up with team progress. | Added short notes for review.
| What are doing today? | Orginzing work. | Updating progress. | Writing documentation. | Reviewing updates with Roaa. | Preparing weekly report.
| Is there anything blocking you? | No | No | No | No | No

## Week 2
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you do yesterday? | Organized a suitable time for the team members to meet | Start sprint planning meeting | Design interface for display patients medical records | Develop the functionality of appointment booking | Implementing and developing the functionalities of appointment booking
| What are doing today? | Start sprint planning meeting | Design interface for display patients medical records | Develop the functionality of appointment booking | Implementing and developing the functionalities of appointment booking | Test all my tasks
| Is there anything blocking you? | No | No | Time isn't enough | No | No
Roaa | What did you do yesterday? | Reviewed our work according to the feedback provided by the instructor | Presenting the improvements to the team. | Build interface for registering hospital staff | Build interface for patients registration | Design UI for selecting doctor and viewing available slots
| What are doing today? | Presenting the improvements to the team. | Build interface for registering hospital staff | Build interface for patients registration | Design UI for selecting doctor and viewing available slots | Test all my tasks
| Is there anything blocking you? | No | No | No | No | No
Sumaiya | What did you do yesterday? | Define what needs to be achieved during the sprint | Complete arrangement of sprint tasks. | design interface to display patients medical record | Develop the functionality to retrieve and display patient list | Continue Developing the functionality to retrieve and display patient list
| What are doing today? | Complete arrangement of sprint tasks. | design interface to display patients medical record | Develop the functionality to retrieve and display patient list | Continue Developing the functionality to retrieve and display patient list | Test all my tasks
| Is there anything blocking you? | No | No | Network issues | No | No
Bushra | What did you do yesterday? | Update the product backlog | Presenting the new product backlog | integrate the system with database | implement a search /filter for appointment based on date or patient | Develop backend API to fetch doctors' availability
| What are doing today? | Presenting the new product backlog | integrate the system with database | implement a search /filter for appointment based on date or patient | Develop backend API to fetch doctors' availability | Test all my tasks
| Is there anything blocking you? | No | No | No | No | No

## Week 3
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you do yesterday? | Test all my tasks | Design interface to display patients medical record | Continue working on medical records display | Test medical records interface | Review appointment booking
| What are doing today? | Design interface to display patients medical record | Continue working on medical records display | Test medical records interface | Review appointment booking | Prepare for sprint review
| Is there anything blocking you? | No | No | No | No | No
Roaa | What did you do yesterday? | Test all my tasks | Build interface for registering hospital staff | Build interface for patients registration | Test registration interfaces | Design UI for selecting doctor
| What are doing today? | Build interface for registering hospital staff | Build interface for patients registration | Test registration interfaces | Design UI for selecting doctor | Review my work
| Is there anything blocking you? | No | No | No | No | No
Sumaiya | What did you do yesterday? | Test all my tasks | Develop functionality to retrieve patient list | Continue patient list development | Test patient list | Develop backend API to fetch doctors availability
| What are doing today? | Develop functionality to retrieve patient list | Continue patient list development | Test patient list | Develop backend API to fetch doctors availability | Review APIs
| Is there anything blocking you? | No | No | No | No | No
Bushra | What did you do yesterday? | Test all my tasks | integrate the system with database | implement search filter for appointment | Test database integration | Review backend work
| What are doing today? | integrate the system with database | implement search filter for appointment | Test database integration | Review backend work | Prepare sprint demo
| Is there anything blocking you? | No | No | No | No | No

## Week 4
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you do yesterday? | Prepare for sprint review | Present my work | Attend sprint review meeting | Collect feedback | Attend retrospective
| What are doing today? | Present my work | Attend sprint review meeting | Collect feedback | Attend retrospective | Plan Sprint 2
| Is there anything blocking you? | No | No | No | No | No
Roaa | What did you do yesterday? | Review my work | Prepare demo | Present at sprint review | Discuss improvements | Join retrospective
| What are doing today? | Prepare demo | Present at sprint review | Discuss improvements | Join retrospective | Review Sprint 2 backlog
| Is there anything blocking you? | No | No | No | No | No
Sumaiya | What did you do yesterday? | Review APIs | Prepare for review | Demo my features | Get feedback | Retrospective meeting
| What are doing today? | Prepare for review | Demo my features | Get feedback | Retrospective meeting | Select Sprint 2 tasks
| Is there anything blocking you? | No | No | No | No | No
Bushra | What did you do yesterday? | Prepare sprint demo | Present backend | Sprint review | Facilitate retrospective | Prepare Sprint 2 backlog
| What are doing today? | Present backend | Sprint review | Facilitate retrospective | Prepare Sprint 2 backlog | Assign tasks
| Is there anything blocking you? | No | No | No | No | No

## Week 5
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you do yesterday? | Plan Sprint 2 | ID and Insurance provider screen | Continue insurance screen | Insurance validation API integration | Test insurance validation
| What are doing today? | ID and Insurance provider screen | Continue insurance screen | Insurance validation API integration | Test insurance validation | Review insurance module
| Is there anything blocking you? | No | No | No | API issues | No
Roaa | What did you do yesterday? | Review Sprint 2 backlog | Build response interface accepted/rejected | Continue response interface | Connect UI with insurance response API | Test response interface
| What are doing today? | Build response interface accepted/rejected | Continue response interface | Connect UI with insurance response API | Test response interface | Employee management screen
| Is there anything blocking you? | No | No | No | No | No
Sumaiya | What did you do yesterday? | Select Sprint 2 tasks | Insurance validation API integration | Continue API work | Discount calculation logic | Apply discount in payment screen
| What are doing today? | Insurance validation API integration | Continue API work | Discount calculation logic | Apply discount in payment screen | Test discount
| Is there anything blocking you? | No | No | Connection timeout | No | No
Bushra | What did you do yesterday? | Assign tasks | Build lab results upload interface | Continue Building lab results upload interface | Backend integration to store lab results | Test upload
| What are doing today? | Build lab results upload interface | Continue Building lab results upload interface | Backend integration to store lab results | Test upload | Lab test request form
| Is there anything blocking you? | No | No | No | No | No

## Week 6
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you do yesterday? | Review insurance module | Payment gateway integration | Continue payment integration | Payment receipt and confirmation | Test payment
| What are doing today? | Payment gateway integration | Continue payment integration | Payment receipt and confirmation | Test payment | Prescription viewing page
| Is there anything blocking you? | No | No | No | Payment sandbox issues | No
Roaa | What did you do yesterday? | Employee management screen | Continue employee screen | Insurance company management module | Test employee management | Chat UI
| What are doing today? | Continue employee screen | Insurance company management module | Test employee management | Chat UI | Continue chat interface
| Is there anything blocking you? | No | No | No | No | No
Sumaiya | What did you do yesterday? | Test discount | Billing report generator | Continue report generator | Payment report and export options | Test reports
| What are doing today? | Billing report generator | Continue report generator | Payment report and export options | Test reports | Email template and UI
| Is there anything blocking you? | No | No | No | No | No
Bushra | What did you do yesterday? | Lab test request form | Continue lab request | Link test results to patient record | Test lab module | Backend chat service connection
| What are doing today? | Continue lab request | Link test results to patient record | Test lab module | Backend chat service connection | Email sending service integration
| Is there anything blocking you? | No | No | No | No | No

## Week 7
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you do yesterday? | Prescription viewing page | Continue prescription page | Link lab results to patient portal | Test prescription and lab results | Review all my work
| What are doing today? | Continue prescription page | Link lab results to patient portal | Test prescription and lab results | Review all my work | Prepare final demo
| Is there anything blocking you? | No | No | No | No | No
Roaa | What did you do yesterday? | Continue chat interface | Test chat UI | Backend chat service connection | Test chat service | Review all features
| What are doing today? | Test chat UI | Backend chat service connection | Test chat service | Review all features | Final testing
| Is there anything blocking you? | No | No | No | No | No
Sumaiya | What did you do yesterday? | Email template and UI | Continue email template | Email sending service integration | Test email service | Review billing and reports
| What are doing today? | Continue email template | Email sending service integration | Test email service | Review billing and reports | Sprint 2 review
| Is there anything blocking you? | No | No | No | No | No
Bushra | What did you do yesterday? | Email sending service integration | Test email integration | Review all backend work | System testing | Prepare presentation
| What are doing today? | Test email integration | Review all backend work | System testing | Prepare presentation | Sprint 2 retrospective
| Is there anything blocking you? | No | No | No | No | No