## Final Product Backlog3
PRODUCT BACKLOG
PRODUCT BACKLOG | [7 empty] | STATUS | PRIORITY
ID | AS A … | I WANT TO … | SO THAT … | Size | PRIORITY | Number of SPRINTs | STATUS | Not Started | High
1 | IT Administrator | register hospital staff | I can manage user access and system roles | S | High | 1 | Complete | In Progress | Medium
2 | Patient | register and create an account | I can book appointments and access my medical records | S | High | 1 | Complete | Complete | Low
3 | Patient | book an appointment online | so that I can choose a convenient time with my preferred doctor | L | High | 1 | Complete | Overdue
3.1 | Patient | view a list of available doctors | I can choose one based on my preferences | S | High | 1 | Complete | Overdue
3.2 | Patient | be able to select an available time slot for an appointment with the doctor | I can choose a time that suits me. | S | High | 1 | Complete | Overdue
3.3 | Patient | receive an email confirmation of my appointment | I have a record of it. | S | High | 1 | Complete
4 | Doctor | view my patient list and appointments | I manage my daily schedule efficiently | M | High | 1 | Complete | On Hold
5 | Doctor | view a patient’s full medical record before treatment | so that I can make accurate diagnoses and decisions | M | High | 1 | Complete
6 | Patient | enter my insurance information in the hospital website | So that I can check if my insurance is valid and see my coverage amount | L | High | 2 | Complete
6.1 | Patient | enter my ID number and insurance company name on the hospital’s website | I can check if the insurance is valid to me or not. | S | High | 2 | Complete
6.2 | Patient | receive a response through an interface that tells me whether my request is accepted or rejected | I can know if the insurance will cover my medical expenses. | S | High | 2 | Complete
6.3 | Patient ( note* if if the insurance is valid ) | the discount to be applied to the total amount due when paying the bill | I can benefit from the insurance coverage. | S | High | 2 | Complete
7 | Lab Technician | upload test results to the system | doctors can access lab data without delay | S | High | 2 | Complete
8 | hospital manager | be able to supervise and view all employee details and supported insurance companies in the hospital system | I can ensure smooth operations | S | Medium | 2 | Complete
9 | Accountant Administrator | generate billing and payment reports | I can track hospital revenue and patient payments | S | Medium | 2 | Complete
10 | Doctor | request lab tests and view results digitally | I can make faster medical decisions | S | Medium | 2 | Complete
11 | Patient | pay medical bills online securely (visa , mada , apple pay) | I can complete my payments easily from home | S | Medium | 2 | Complete
12 | Patient | view prescriptions and lab results online | I can stay informed about my health status | S | Medium | 2 | Complete
13 | Patient | contact customer service via Chat | I can get assistance with my medical queries or issues | S | Medium | 2 | Complete
14 | Patient | receive appointment reminders via email | I won't forget my scheduled visits | S | Low | 1 | Complete
15 | Marketing Administrator | send promotional offers to patients via email | I can attract more customers | S | Low | 2 | Complete
TOTAL | [5 empty] | 33

## proudect Backlog2
PRODUCT BACKLOG
PRODUCT BACKLOG
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | Number of SPRINTs | STATUS | STATUS | PRIORITY
1 | Administrator | register doctors, nurses, and staff | I can manage user access and system roles | High | 1 | Complete | Not Started | High
2 | Doctor | view a patient’s full medical record before treatment | so that I can make accurate diagnoses and decisions | High | 1 | Complete | In Progress | Medium
3 | Doctor | view my patient list and appointments | I manage my daily schedule efficiently | High | 1 | In Progress | Complete | Low
4 | Doctor | request lab tests and view results digitally | I can make faster medical decisions | Medium | 1 | In Progress | Overdue
5 | Patient | register and create an account | I can book appointments and access my medical records | High | 1 | Complete | On Hold
6 | Patient | view prescriptions and lab results online | I can stay informed about my health status | Medium | 2 | In Progress
7 | Patient | I want to book an appointment online | so that I can choose a convenient time with my preferred doctor | High | 2 | In Progress
8 | Receptionist | schedule appointments for patients | I can organize doctor availability and bookings | Low | 1 | In Progress
9 | Nurse | update patient's vital signs and daily progress | doctors can monitor patient condition in real life | High | 1 | Not Started
10 | Pharmacist | I can ensure that prescriptions are filled correctly | manage and update available medicines in the inventory | Medium | 1 | In Progress
11 | Administrator | I can evaluate efficiency and improve management | generate reports on hospital performance and staff activity | High | 2 | Not Started
12 | Patient | I can complete my payments easily from home | pay medical bills online securely | Medium | 2 | On Hold
13 | Lab Technician | doctors can access lab data without delay | upload test results to the system | High | 2 | Complete
14 | Patient | I won't forget my scheduled visits | receive appointment reminders via SMS or email | Medium | 1 | Overdue
TOTAL |  |  |  |  | 19

## Proudct Backlog1
PRODUCT BACKLOG
PRODUCT BACKLOG
ID | AS A ... | I WANT TO ... | SO THAT ... | PRIORITY | Number of SPRINTs | STATUS
1 | Administrator | register doctors, nurses, and staff | I can manage user access and system roles | High | 1 | Complete
2 | Patient | register and create an account | I can book appointments and access my medical records | High | 1 | Complete
3 | Patient | book an appointment online | so that I can choose a convenient time with my preferred doctor | High | 1 | Complete
4 | Doctor | view my patient list and appointments | I manage my daily schedule efficiently | High | 1 | In Progress
5 | Doctor | view a patient's full medical record before treatment | so that I can make accurate diagnoses and decisions | High | 1 | In Progress
6 | Patient | enter my insurance information in the hospital application | So that I can check if my insurance is valid and see my coverage amount | High | 1 | Not Started
7 | Lab Technician | upload test results to the system | doctors can access lab data without delay | High | 2 | Not Started
8 | Nurse | update patient's vital signs and daily progress | doctors can monitor patient condition in real life | High | 1 | Not Started
9 | Accountant | generate billing and payment reports | I can track hospital revenue and patient payments | Medium | 2 | Not Started
10 | Doctor | request lab tests and view results digitally | I can make faster medical decisions | Medium | 2 | Not Started
11 | Pharmacist | manage and update available medicines in the inventory | I can ensure that prescriptions are filled correctly | Medium | 1 | Not Started
12 | Administrator | generate reports on hospital performance and staff activity | I can evaluate efficiency and improve management | Medium | 2 | Not Started
13 | Patient | pay medical bills online securely | I can complete my payments easily from home | Medium | 2 | Not Started
14 | Patient | view prescriptions and lab results online | I can stay informed about my health status | Medium | 2 | Not Started
15 | Patient | receive appointment reminders via SMS or email | I won't forget my scheduled visits | Low | 1 | Not Started
16 | Doctor | communicate with other doctors through secure messaging | I can discuss patient cases easily! | Low | 2 | Not Started
TOTAL | [5 empty] | 24