## Sprint Backlog2
SPRINT BACKLOG
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
11/22/25 | 2025-12-11 | 264 |  | 150 |  | 114
SPRINT GOAL | Write A short statement of what the team aims to achieve during the sprint.
SPRINT TRACKING |  |  |  |  | Start of the Sprint Date
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | Day;20 | DAY 21
User Story 1 Name:As a patient i want to enter my ID number in insurance company name on the hospital’s website, so that i can check if my insurance is valid to me or not. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 ID and Insurance provider input screen | Member's Name:Joud | 10 | 5 | 5 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Insurance validation API integration | Member's Name: Sumaiya | 12 | 6 | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 2 Name: As a patient I want receive a response from the insurance company through an interface that tells me whether my request is accepted or rejected so that i can know if the insurance will cover my medical expenses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.1 Build response interface ( accepted/rejected) | Member's Name: Roaa | 14 | 6 | 8 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Task 2.2 Connect UIwith insurance response API | Member's Name: Bushra | 16 | 9 | 7 | 1 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 3 Name: As a patient ( note* if the insurance valid ) I want to the discount to be applied to the total amount sue when paying the bill so that i can benefit from the insurance coverage |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Task 3.1 Discount calculation logic | Member's Name: Sumaiya | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3.2 Apply discount in payment screen | Member's Name: Joud | 10 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 4 Name: As a lab technician I want to upload test result to the system so that doctor can access lab data without delay. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.1 Uplod module (UI+file validation) | Member's Name: Bushra | 14 | 7 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.2 Backebd integration to store lab results | Member's Name: Sumaiya | 16 | 9 | 7 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 5 Name:As a hospital manager i want to be able to service and view all employee details and supported insurance companies in the hospital system so that i can ensure smooth operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.1 Employee management screen | Member's Name: Roaa | 12 | 8 | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.2 Insurance company management module | Member's Name: Bushra | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 6 Name: As a Accountant administrator i want to generate billing and payment reports so that i cant track hospital revenue and patient payments |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.1 Billing report generator | Member's Name: Joud | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.2 Payment report and export options | Member's Name: Bushra | 12 | 5 | 7 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 7 Name:As a doctor i want to request lab test and view result digitally so that is can make faster medical decision |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 7.1 Lab test request form | Member's Name: Roaa | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
Task 7.2 Link test results to patient record | Member's Name: Sumaiya | 14 | 8 | 6 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 8 Name:As a patient i want to pay medical bills online securely (visa, mada, apple pay), so that is can complete my payments easily from home. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 8.1 Payment gateway integration | Member's Name: Sumaiya | 16 | 8 | 8 | 1 | 1 | 2 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 8.2 Payment recepitand confirmation | Member's Name: Joud | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 9 Name:As a patient i want to view prescription and lab results online so that i can stay informed about my health status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 9.1 Proscription biewing page | Member's Name: Roaa | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Task 9.2 Link lab results to patient portal | Member's Name: Bushra | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
User Story 10 Name:As a patient i want to contact customer service via chat so that i can get assistance with my medical queries or issues. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 10.1 chat UI | Member's Name: Joud | 10 | 6 | 4 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 10.2 Backend chat service connection | Member's Name: Sumaiya | 14 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 11 Name :As a marketing administrator i want to send promotional offers to patients via email so that i can attract more customers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 11.1 Email tamplate and UI | Member's Name: Bushra | 8 | 5 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Task 11.2 Email sending service integration | Member's Name: Sumaiya | 12 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
TOTAL |  | 264 | 150 | 114
Add More Tasks and User Stories if You Need to

## Sprint Backlog1
SPRINT BACKLOG
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
2025-10-16 | 2025-10-16 | 61 |  | 43 |  | 18
SPRINT GOAL | the team aims to build the core functionalities of the system to ensure smooth workflow
SPRINT TRACKING |  |  |  |  | Start of the Sprint Date
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
User Story 1 Name: as an Administrator I want to register hospital staff so that I can manage user access and system roles |  | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Build interface for registering hospitoal staff | Member's Name: Roaa | 3 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 integrate the system with database | Member's Name: bushra | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 2 Name:as a doctor I want to view full medical records of patients befor treatment so that I can make accurate diagnoses and decisions |  | 4 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.1 design interface for display patients medical records | Member's Name: joud | 3 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 3 Name: as a patient I want to register and create an account so that I can book appointments and access my medical records |  | 8 | 6 | 2 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3.1 devolope the functionalitiy of appointment booking | Member's Name :joud | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3.2 build interface for patients regstration and integrate it withn database | Member's Name: Roaa | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3.3 design interface to display patients medical record | Member's Name: sumaiya | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 4 Name: as a doctor I want to view my patient list and appoinments so that I mange my daily schudels efficiently |  | 6 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.1 Develop the functionality to retrieve and display patient list | Member's Name :Sumayia | 4 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.2 implement a search /filter for appointment based on date or patient | Member's Name :bushra | 5 | 2 | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 5 Name: as a patient I want to book appointments online so that I can choose a convenient time with my preferred doctor |  | 12 | 8 | 4 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.1 Design UI for selecting doctor and viewing available slots | Member's Name :Roaa | 4 | 3 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.2 Develop backend API to fetch doctors' availability | Member's Name :Sumayia | 8 | 5 | 3 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 61 | 43 | 18